Yemen SIG

Quarterly meeting

Update

Tuesday 17th March 2020

Update YMHP

- On 5th November 2019, we received £8,390, 58% of the estimated cost of the project from the Festival Medical Services. The project estimated cost was £14,409.

- We are working with a local website developer in Liverpool to finalise the website. The first draft of the Yemen Mobile Health website will be ready for sharing week beginning 23rd March 2020.

- We are exploring the right solution and a reasonable price for the technical WhatsApp automation through an Application Programme Interface (API).

- We are expecting the final modified messages and images this week.

- We will continue apply for funding to enable us complete the project as planned.

## Cholera outbreak update

Oxfam reported 9th March 2020 that the rainy season in Yemen threatens huge cholera spike as conflict hampers efforts to address forgotten crisis.

WHO reported 26th January 2020 that the cumulative total number of suspected cholera cases from 1 January 2018 to 26 January 2020 is 1 262 722, with 1543 associated deaths (CFR 0.12%).

https://reliefweb.int/report/yemen/rainy-season-threatens-huge-cholera-spike-yemen

http://www.emro.who.int/fr/pandemic-epidemic-diseases/cholera/outbreak-update-cholera-in-yemen-26-january-2020.html